## Deployment Plan (hidden)
Oracle/RMS Upgrade 08/08/15
No | Program | Task | Responsible Team | Supoprting Team | Task Owner | Start Date | Est Start Time | End Date | Est End Time | Est Duration | Status | Pre Dependency | Category | Prerequisite | Post Dependency | Service Request # | E-Mail Comm Req | Comments | Error | Action | Notes from Tech team
1 | PRE Task
2 |  | Prepare and download all software in required folder to be ready for installation | DBA | DBA | Venkata | 2015-07-27 |  | 2015-08-03
3 |  | Open change ticket for unix team for sudo access to root for DBA (TCS/Windstream). Change request will also cover server reboots before database upgrade activity starts | DBA | Windstream | Venkata | 2015-07-30 |  | 2015-08-08
4 |  | Get addditional space for backup | Unix Team | DBA | Venkata | 2015-07-30
5 |  | Send out the communication that application will be down and update about the upgrade plan | Amber, Chris C. | Solution team | Chris C. | 2015-08-07 | 10:00 | 2015-08-07 | 17:00 | 7:00
6 |  | Take full backup of RMS, OID and RIB databases on to disk Turn off tape backup (after Thursday night 08/06 batch completion) | DBA | DBA | Venkata | 2015-08-07 | 6:00 | 2015-08-07 | 12:00
7 |  | Confirm nightly batch is complete | Application Support | Batch monitoring team | Ayan | 2015-08-08 | 6.00 AM | 2015-08-08 | 6.05 AM
8 |  | Autosys request ( to stop the autosys agent) - Change ticket | Autosys | RMS Support Team |  | 2015-08-08 | 6:00 | 2015-08-08 | 6.15 AM
9 |  | Stop ESB flows into RMS | ESB Team | ESB Team | ESB Support | 2015-08-08 | 6.00AM | 2015-08-08 | 6.15 AM
10 |  | Bring down the Applications | DBA | DBA | Venkata | 2015-08-08 | 6.30 AM | 2015-08-08 | 6.45 am
11 |  | Reboot RMS/RIB application servers | Unix Team | DBA Team | Venkata | 2015-08-08 | 7.00 AM | 2015-08-08 | 8:00
12 |  | DBA will take additional RMAN backup (incremental) | DBA | DBA | Venkata | 2015-08-08 | 7.00 am | 2015-08-08 | 10:00
13 | Database Upgrade
14 |  | Bring down databases and reboot database server | DBA, Unix Team | DBA | Venkata | 2015-08-08 | 10:00 | 2015-08-08 | 10:30 | 0:30
15 |  | Database upgrade (11.2.0.3.8 to 11.2.0.4.6) | DBA | DBA | Venkata | 2015-08-08 | 10:30 | 2015-08-08 | 6.30 PM
16 |  | Database Completion - Confirmation | DBA | DBA | Venkata | 2015-08-08 | 18:30 | 2015-08-08 | 18:30 | 0:00
17 |  | Start Application (RMS/RIB) | DBA | DBA | Venkata | 2015-08-08 | 18:30 | 2015-08-08 | 19:30
| Smoke Test | Smoke test online application | RMS Support Team | RMS Support Team | Surajit | 2015-08-08 | 19:30 | 2015-08-08 | 20:30
|  | Bring ESB flows up and catch up on inventory feed from legacy | ESB Team | ESB Team | Amjad | 2015-08-08 | 20:30 | 2015-08-08 | 20:45
|  | Smoke test item flow from RMS to PIM (update to existing items) | Business User | Support Team | Krishna | 2015-08-08 | 20:45 | 2015-08-08 | 21:30
|  | Bring up autosys RMS agents | Autosys Team | Support Team | Billy/Bruce | 2015-08-08 | 9.30 PM | 2015-08-08 | 9.45 PM
|  | Release and monitor batch | Support Team | Support Team | Ayan | 2015-08-08 | 9.45 PM | 2015-08-09 | 18:00
17
18
1 | OAM/OID Upgrade
1 | PRE Task | Take OS level back and get confimration from TSM team | DBA | DBA | Venkata | 2015-08-13 | 8:00 | 2015-08-13 | 12:00
1 |  | Add same task as database upgrade for bringing down autosys agent, ESB flows
1 |  | PRE Task - DBA will take RMAN (full) backup for RMS | DBA | DBA | Venkata | 2015-08-14 | 8:00 | 2015-08-14 | 17:00 | 9:00
1 |  | PRE Task - DBA will take RMAN backup for OID | DBA | DBA | Venkata | 2015-08-14 | 8:00 | 2015-08-14 | 17:00 | 9:00
18 |  | PRE Task - DBA will take RMAN backup for RIB | DBA | DBA | Venkata | 2015-08-14 | 8:00 | 2015-08-14 | 17:00 | 9:00
19 |  | PRE Task - Datapump full export of OIDPRD database | DBA | DBA | Venkata | 2015-08-14 | 8:00 | 2015-08-14 | 17:00 | 9:00
Confirm nightly batch is complete
8 |  | Autosys request ( to stop the autosys agent) - Change ticket | Autosys | RMS Support Team |  | 2015-08-15 | 6:00 | 2015-08-15 | 6.15 AM
9 |  | Stop ESB flows into RMS | ESB Team | ESB Team | ESB Support | 2015-08-15 | 6.00AM | 2015-08-15 | 6.15 AM
10 |  | Bring down the Applications | DBA | DBA | Venkata | 2015-08-15 | 6.30 AM | 2015-08-15 | 6.45 am
12 |  | DBA will take additional RMAN backup (incremental) | DBA | DBA | Venkata | 2015-08-15 | 7.00 am | 2015-08-15 | 10:00
#REF! |  | Weblogic Upgrade for OAM 10.3.6 | DBA | DBA | Venkata | 2015-08-15 | 10:00 | 2015-08-15 | 11:30 | 16:00
#REF! |  | OID Upgrade to 11.1.1.7 | DBA | DBA | Venkata | 2015-08-15 | 11:30 | 2015-08-15 | 13:00 | 16:00
|  | OAM Upgrade to 11.1.1.7 | DBA | DBA | Venkata | 2015-08-15 | 13:00 | 2015-08-15 | 2.30 PM
|  | Webgate upgrade to 11.1.1.7 | DBA | DBA | Venkata | 2015-08-15 | 14:30 | 2015-08-15 | 15:30
|  | Webtier upgrade to 11.1.1.7 | DBA | DBA | Venkata | 2015-08-15 | 15:30 | 2015-08-15 | 16:30
|  | Start Applications | DBA | DBA | Venkata | 2015-08-15 | 16:30 | 2015-08-15 | 17:30
|  | Smoke test online application (single sign on) |  |  |  | 2015-08-15 | 17:30 | 2015-08-15 | 18:30
|  | Drop support user and add it back | Business User | Solution team | Surajit | 2015-08-15 | 17:30 | 2015-08-15 | 18:30 | 1:00
|  | Bring ESB flows up and catch up on inventory feed from legacy |  |  |  | 2015-08-15 | 18:30 | 2015-08-15 | 20:30
|  | Smoke test item flow from RMS to PIM (update to existing items) |  |  |  | 2015-08-15 | 18:45 | 2015-08-15 | 19:30
|  | Bring up autosys RMS agents |  |  |  | 2015-08-15 | 20:30 | 2015-08-15 | 20:45
|  | Release and monitor batch |  |  |  | 2015-08-15 | 20:45 | 2015-08-16 | 18:00
1 | RMSPatch Upgrade
1 | Week 3
14 |  | Touch the component : s14269424_item_mfqueue.sql | DBA | Solution team | Venkata | 2015-08-21 | 10:00 | 2015-08-21 | 20:00 | 10:00
15 |  | Touch the component: s14632589_gtt_price_hist_mgn_backup.sql | DBA | Solution team | Venkata | 2015-08-21 | 10:00 | 2015-08-21 | 20:00 | 10:00
16 |  | touch the component : c16458144_form_elements_langs.sql | DBA | Solution team | Venkata | 2015-08-21 | 10:00 | 2015-08-21 | 20:00 | 10:00
17 |  | Touch the component: 000029_s17895039_item_loc.sql | DBA | Solution team | Venkata | 2015-08-21 | 10:00 | 2015-08-21 | 20:00 | 10:00
18 |  | touch the component: 000030_s17895039_item_loc_soh.sql | DBA | Solution team | Venkata | 2015-08-21 | 10:00 | 2015-08-21 | 20:00 | 10:00
19 |  | touch the component: 000020_s18386414_gtt_alloc_order_no.sql | DBA | Solution team | Venkata | 2015-08-21 | 10:00 | 2015-08-21 | 20:00 | 10:00
20 |  | touch the component : 000021_s18386414_gtt_orderhead_order_no.SQL | DBA | Solution team | Venkata | 2015-08-21 | 10:00 | 2015-08-21 | 20:00 | 10:00
21 |  | touch the component: 000033_s17895039_repl_results | DBA | Solution team | Venkata | 2015-08-21 | 10:00 | 2015-08-21 | 20:00 | 10:00
22 |  | touch the component: 000034_s17895039_tran_data_history | DBA | Solution team | Venkata | 2015-08-21 | 10:00 | 2015-08-21 | 20:00 | 10:00
23 |  | touch the component: 000035_s17895039_vat_history | DBA | Solution team | Venkata | 2015-08-21 | 10:00 | 2015-08-21 | 20:00 | 10:00
24 |  | touch the component: 000036_s17895039_week_data | DBA | Solution team | Venkata | 2015-08-21 | 10:00 | 2015-08-21 | 20:00 | 10:00
#REF! |  | touch the component: s14825754_rpm_stage_publish_data.sql | DBA | Solution team | Venkata | 2015-08-21 | 10:00 | 2015-08-21 | 20:00 | 10:00
#REF! |  | touch the component: s15983234_rpm_system_options.sql | DBA | Solution team | Venkata | 2015-08-21 | 10:00 | 2015-08-21 | 20:00 | 10:00
#REF! |  | touch the component: s15983265_rpm_duplicate_fr_data.sql | DBA | Solution team | Venkata | 2015-08-21 | 10:00 | 2015-08-21 | 20:00 | 10:00
#REF! |  | touch the component: s15983265_rpm_missing_timeline.sql | DBA | Solution team | Venkata | 2015-08-21 | 10:00 | 2015-08-21 | 20:00 | 10:00
#REF! |  | touch the component: s15983342_rpm_bulk_cc_pe_thread.sql | DBA | Solution team | Venkata | 2015-08-21 | 10:00 | 2015-08-21 | 20:00 | 10:00
#REF! |  | touch the component: s15988621_rpm_clearance_pl_stage.sql | DBA | Solution team | Venkata | 2015-08-21 | 10:00 | 2015-08-21 | 20:00 | 10:00
#REF! |  | touch the component: s15988621_rpm_clearance_skulist.sql | DBA | Solution team | Venkata | 2015-08-21 | 10:00 | 2015-08-21 | 20:00 | 10:00
#REF! |  | touch the component: s15988621_rpm_cs_promo_fr_pl_stage.sql | DBA | Solution team | Venkata | 2015-08-21 | 10:00 | 2015-08-21 | 20:00 | 10:00
#REF! |  | touch the component: s15988621_rpm_future_retail_pl_stage.sql | DBA | Solution team | Venkata | 2015-08-21 | 10:00 | 2015-08-21 | 20:00 | 10:00
#REF! |  | touch the component: s15988621_rpm_merch_list_detail.sql | DBA | Solution team | Venkata | 2015-08-21 | 10:00 | 2015-08-21 | 20:00 | 10:00
#REF! |  | touch the component: s15988621_rpm_price_change_skulist.sql | DBA | Solution team | Venkata | 2015-08-21 | 10:00 | 2015-08-21 | 20:00 | 10:00
#REF! |  | touch the component: s15988621_rpm_promo_dtl_skulist.sql | DBA | Solution team | Venkata | 2015-08-21 | 10:00 | 2015-08-21 | 20:00 | 10:00
#REF! |  | touch the component: s15988621_rpm_promo_il_expl_pl_stage.sql | DBA | Solution team | Venkata | 2015-08-21 | 10:00 | 2015-08-21 | 20:00 | 10:00
#REF! |  | touch the component: s15988621_rpm_stg_upd_rst_on_clr_rmv.sql | DBA | Solution team | Venkata | 2015-08-21 | 10:00 | 2015-08-21 | 20:00 | 10:00
#REF! |  | touch the component: s15989265_rpm_dept_aggregation.sql | DBA | Solution team | Venkata | 2015-08-21 | 10:00 | 2015-08-21 | 20:00 | 10:00
#REF! |  | touch the component: s15989265_rpm_pre_me_aggregation.sql | DBA | Solution team | Venkata | 2015-08-21 | 10:00 | 2015-08-21 | 20:00 | 10:00
#REF! |  | touch the component: s16002097_rpm_stage_item_loc_clean.sql | DBA | Solution team | Venkata | 2015-08-21 | 10:00 | 2015-08-21 | 20:00 | 10:00
#REF! |  | touch the component: s16232269_rpm_rollup_gtt.sql | DBA | Solution team | Venkata | 2015-08-21 | 10:00 | 2015-08-21 | 20:00 | 10:00
#REF! |  | touch the component: s16284908_rpm_item_loc.sql | DBA | Solution team | Venkata | 2015-08-21 | 10:00 | 2015-08-21 | 20:00 | 10:00
#REF! |  | touch the component: s16394085_rpm_area_diff.sql | DBA | Solution team | Venkata | 2015-08-21 | 10:00 | 2015-08-21 | 20:00 | 10:00
#REF! |  | touch the component: s16394085_rpm_area_diff_prim.sql | DBA | Solution team | Venkata | 2015-08-21 | 10:00 | 2015-08-21 | 20:00 | 10:00
#REF! |  | touch the component: s17313274_rpm_merch_list_head.sql | DBA | Solution team | Venkata | 2015-08-21 | 10:00 | 2015-08-21 | 20:00 | 10:00
#REF! |  | touch the component: s17313274_rpm_pc_ticket_request.sql | DBA | Solution team | Venkata | 2015-08-21 | 10:00 | 2015-08-21 | 20:00 | 10:00
#REF! |  | touch the component: s17313274_rpm_price_change.sql | DBA | Solution team | Venkata | 2015-08-21 | 10:00 | 2015-08-21 | 20:00 | 10:00
#REF! |  | touch the component: s17526135_rpm_bulk_cc_pe_thread.sql | DBA | Solution team | Venkata | 2015-08-21 | 10:00 | 2015-08-21 | 20:00 | 10:00
#REF! |  | touch the component: s17526135_rpm_clearance_payload.sql | DBA | Solution team | Venkata | 2015-08-21 | 10:00 | 2015-08-21 | 20:00 | 10:00
#REF! |  | touch the component: s17526135_rpm_price_chg_payload.sql | DBA | Solution team | Venkata | 2015-08-21 | 10:00 | 2015-08-21 | 20:00 | 10:00
#REF! |  | touch the component: s17526135_rpm_price_event_payload.sql | DBA | Solution team | Venkata | 2015-08-21 | 10:00 | 2015-08-21 | 20:00 | 10:00
25 |  | 000037_s16722942_pos_mods | DBA | Solution team | Venkata | 2015-08-21 | 10:00 | 2015-08-21 | 20:00 | 10:00
5 |  | Take a back of all Pro*C component list in src directory ( to a back up directory) | DBA | DBA | Venkata | 2015-08-19 | 8:00 | 2015-08-19 | 17:00 | 9:00
6 |  | Take a back of all Pro*C component list in bin directory ( to a back up directory) | DBA | DBA | Venkata | 2015-08-19 | 8:00 | 2015-08-19 | 17:00 | 9:00
7 |  |  | DBA | DBA | Venkata | 2015-08-19 | 8:00 | 2015-08-19 | 17:00 | 9:00
8 |  | Take a back of all .ksh script (to a abck up directory) | DBA | DBA | Venkata | 2015-08-19 | 8:00 | 2015-08-19 | 17:00 | 9:00
9 |  | Take a back of all FORMS component list in src directory (to a abck up directory) | DBA | DBA | Venkata | 2015-08-19 | 8:00 | 2015-08-19 | 17:00 | 9:00
10 |  | Take a back of all FORMS component list in bin directory (to a abck up directory) | DBA | DBA | Venkata | 2015-08-19 | 8:00 | 2015-08-19 | 17:00 | 9:00
1 | Index planning | Index taking long time needs to be planned | DBA | DBA | Venkata | 2015-08-19 | 20:00 | 2015-08-19 | 8:00 | 12 HR
2 |  | Create Index which is running for a Long time ( ItemLoc table Index [000029_s17895039_item_loc.sql] | DBA | DBA | Venkata | 2015-08-19 | 20:00 | 2015-08-20 | 8:00 | 12 HR
3 |  | Create Index which is running for a Long time ( ItemLoc SOH table Index [000030_s17895039_item_loc_soh.sql] | DBA | DBA | Venkata | 2015-08-19 | 20:00 | 2015-08-20 | 8:00 | 12 HR
4 |  | Create Index (Shipment_I6)which is running for a Long time ( SHIPSKU table Index ) | DBA | DBA | Venkata | 2015-08-19 | 20:00 | 2015-08-20 | 8:00 | 2 Min | [7 empty] | Ayan to check on this
1 | PRE Task | Take OS level back and get confimration from TSM team | DBA | DBA | Venkata | 2015-08-20 | 8:00 | 2015-08-20 | 12:00
1 |  | PRE Task - DBA will take RMAN (full) backup for RMS | DBA | DBA | Venkata | 2015-08-20 | 8:00 | 2015-08-20 | 17:00 | 9:00
1 |  | PRE Task - DBA will take RMAN backup for OID | DBA | DBA | Venkata | 2015-08-20 | 8:00 | 2015-08-20 | 17:00 | 9:00
1 |  | PRE Task - DBA will take RMAN backup for RIB | DBA | DBA | Venkata | 2015-08-20 | 8:00 | 2015-08-20 | 17:00 | 9:00
|  | Confirm nightly batch is complete |  | RMS Support Team |  | 2015-08-21 | 6.00 AM | 2015-08-21 | 6:30
8 |  | Autosys request ( to stop the autosys agent) - Change ticket | Autosys | RMS Support Team |  | 2015-08-21 | 6:30 | 2015-08-21 | 6:45
9 |  | Stop ESB flows into RMS | ESB Team | ESB Team | ESB Support | 2015-08-21 | 6:45 | 2015-08-21 | 7:00
10 |  | Bring down the Applications | DBA | DBA | Venkata | 2015-08-21 | 6.30 AM | 2015-08-21 | 6.45 am
12 |  | DBA will take additional RMAN backup (incremental) | DBA | DBA | Venkata | 2015-08-21 | 7.00 am | 2015-08-21 | 10:00
5 | PRE RMS UPGRADE | Drop the custom index SHIPMENT_BI5 and run the base index. | DBA | Solution team | Venkata | 2015-08-21 | 10:00 | 2015-08-21 | 11:00 | 16 HR | [7 empty] | Before upgrade starts
6 |  | Drop the index SHIPMENT_I6 on table Shipment; this will be created by 000007_s18148141_shipment.sql | DBA | Solution team | Venkata | 2015-08-21 | 10:00 | 2015-08-21 | 11:00 | 1:00 | [7 empty] | Before upgrade starts
7 |  | Drop the index POS_MODS_I5 on table POS_MODS; this will be created by 000008_s18385119_pos_mods.sql | DBA | Solution team | Venkata | 2015-08-21 | 10:00 | 2015-08-21 | 11:00 | 1:00 | [7 empty] | Before upgrade starts
8 |  | Drop the index IM_MANUAL_GROUP_RECEIPTS_I1 on table IM_MANUAL_GROUP_RECEIPTS; this index will be created by s18067986_im_manual_group_receipts.sql | DBA | Solution team | Venkata | 2015-08-21 | 10:00 | 2015-08-21 | 11:00 | 1:00 | [7 empty] | Before upgrade starts
9 |  | 000040_s17895039_item_supp_country_loc.sql - Modiy the script, commenting out the intial droping Foreign keys Commented line ALTER TABLE BUYER_WKSHT_MANUAL DROP CONSTRAINT BWM_ISL_FK ALTER TABLE COST_SUSP_SUP_DETAIL_LOC DROP CONSTRAINT CSS_ISL_FK commented after running script for other changes | DBA | Solution team | Venkata | 2015-08-21 | 10:00 | 2015-08-21 | 11:00 | 1:00 | [7 empty] | Before upgrade starts
10 |  | c16027117_l10n_flex_extension_tran_setup.sql Action:Production have nullable columns. So we want to make this as Nullable Yes. | DBA | Solution team | Venkata | 2015-08-21 | 10:00 | 2015-08-21 | 11:00 | 1:00
11 |  | c14350813_cost_chg_reason.sql - Prepare a script to handle the description. | DBA | Solution team | Venkata | 2015-08-21 | 10:00 | 2015-08-21 | 11:00 | 1:00
12 |  | UPDATE CFA_ATTRIB SET LOWEST_ALLOWED_VALUE = null, HIGHEST_ALLOWED_VALUE = null where attrib_id in (8,120); | DBA | Solution team | Venkata | 2015-08-21 | 10:00 | 2015-08-21 | 11:00 | 1:00
|  | Database Schema Upgrade - Upgrade RMSAPPS to 13.2.8. This include executing DB scripts for RMS, RPM, REIM,RMS-ALLOC, RIB | DBA | DBA |  | 2015-08-21 | 11:00 | 2015-08-22 | 0:00
|  | Create new Domain for Allocation 13.3.1 | Middleware | DBA | Avinash | 2015-08-21 | 12:00 | 2015-08-21 | 0:00
|  | RIB 13.2.8 Upgrade | DBA | DBA |  | 2015-08-21 | 12:00 | 2015-08-21 | 15:00 | [8 empty] | Review to see if there is any dependency on RMS upgrade (above task)
|  | RMS Application Upgrade to 13.2.8 | DBA | DBA |  | 2015-08-22 | 0:00 | 2015-08-22 | 5:00
|  | REIM Upgrade 13.2.8 | DBA | DBA |  | 2015-08-22 | 5:30 | 2015-08-22 | 7:30
|  | RPM Upgrade to 13.2.8 | DBA | DBA |  | 2015-08-22 | 7:30 | 2015-08-22 | 8:30
|  | Allocation upgrade 13.3.1.0.3 | DBA |  |  | 2015-08-22 | 8:30 | 2015-08-22 | 10:30
|  | Code migration for code retrofit | DBA | DBA |  | 2015-08-22 | 10:30 | 2015-08-22 | 14:30 | [8 empty] | Check RMS packages to see if they can be started at the same time when REIM, RPM and allocation deployment is runing
|  | Code validation by application team |  |  |  | 2015-08-22 | 14:30 | 2015-08-22 | 15:30
|  | Smoke online application | Application Team | Business Team |  | 2015-08-22 | 3:30 | 2015-08-22 | 16:30
|  | Bring ESB outbound flows up |  |  |  | 2015-08-22 | 16:30 | 2015-08-22 | 17:00
|  | Smoke test item flow from RMS to PIM (update to existing items) Smoke any other transactions (like PO, transfer, RTV..) |  |  |  | 2015-08-22 | 17:00 | 2015-08-22 | 19:00
|  | Bring ESB inbound flows up and catch up on inventory feed from legacy |  |  |  | 2015-08-22 | 19:00 | 2015-08-22 | 22:00
|  | Bring up autosys RMS agents |  |  |  | 2015-08-15 | 22:00 | 2015-08-15 | 22:30
|  | Release and monitor batch |  |  |  | 2015-08-15 | 20:45 | 2015-08-16 | 18:00
2 | Java Version Push |  | Infra | Solution Team | April | 2015-08-21 | 22:00 | 2015-08-21 | 23:00 | 1:00
3 |  | Make sure ReIM Server level java is set properly to java 1.7  Java: JDK 1.7.0+ 64 bit | Infra | Solution Team | April | 2015-08-21 | 22:00 | 2015-08-21 | 23:00 | 1:00
4 |  |  | DBA | DBA | Venkata | 2015-08-19 | 8:00 | 2015-08-19 | 17:00 | 9:00
Detailed tasks
13 | RMS
#REF! |  | Recompile all the objects to make sure no INVALID object present | DBA | Solution team | Venkata | 2015-08-21 | 10:00 | 2015-08-21 | 20:00 | 10:00
#REF! | RIB | Upgrade RIB DB to 13.2.6, 13.2.7, 13.2.8 | DBA | Solution team | Venkata | 2015-08-21 | 10:00 | 2015-08-21 | 20:00 | 10:00
#REF! |  | Script failure script (if any) | DBA | Solution team | Venkata | 2015-08-21 | 10:00 | 2015-08-21 | 20:00 | 10:00
#REF! | RPM | Upgrade RMS database for RPM DB scripts - to 13.2.6, 13.2.7, 13.2.8 | DBA | Solution team | Venkata | 2015-08-21 | 10:00 | 2015-08-21 | 20:00 | 10:00
#REF! |  | s17653209_rpm_bulk_cc_pe_item.sql Action: Rename existing RPM_BULK_CC_PE_ITEM_I2 to RPM_BULK_CC_PE_ITEM_I4 and execute the base as RPM_BULK_CC_PE_ITEM_I2. | DBA | Solution team | Venkata | 2015-08-21 | 10:00 | 2015-08-21 | 20:00 | 10:00
#REF! |  | s16394085_rpm_zone_future_retail.sql | DBA | Solution team | Venkata | 2015-08-21 | 10:00 | 2015-08-21 | 20:00 | 10:00
#REF! | ReIM | touch the component: s16091844_0001_im_doc_head.sql | DBA | Solution team | Venkata | 2015-08-21 | 10:00 | 2015-08-21 | 20:00 | 10:00
#REF! |  | s18067986_im_manual_group_receipts.sql : Inittran has been changed | DBA | Solution team | Venkata | 2015-08-21 | 10:00 | 2015-08-21 | 20:00 | 10:00
#REF! | Run the RMS POST script after the upgrade |  | DBA | Solution team | Venkata | 2015-08-21 | 10:00 | 2015-08-21 | 20:00 | 10:00
#REF! |  | 3) Run the below query next, 3.a. UPDATE CFA_ATTRIB SET LOWEST_ALLOWED_VALUE = 0 WHERE attrib_id = 120; | DBA | Solution team | Venkata | 2015-08-21 | 10:00 | 2015-08-21 | 20:00 | 10:00
#REF! |  | 3.b. UPDATE CFA_ATTRIB SET LOWEST_ALLOWED_VALUE = 0, HIGHEST_ALLOWED_VALUE = 999 WHERE attrib_id = 8; | DBA | Solution team | Venkata | 2015-08-21 | 10:00 | 2015-08-21 | 20:00 | 10:00
#REF! | Rebuild the Indexes |  | DBA | Solution team | Venkata | 2015-08-21 | 10:00 | 2015-08-21 | 20:00 | 10:00
#REF! |  | Rebuild the index PK_SKULIST_DETAIL (--ALTER INDEX <index name> REBUILD ONLINE) | DBA | Solution team | Venkata | 2015-08-21 | 10:00 | 2015-08-21 | 20:00 | 10:00
#REF! |  | Rebuild the index PK_DIVISION | DBA | Solution team | Venkata | 2015-08-21 | 10:00 | 2015-08-21 | 20:00 | 10:00
#REF! |  | Rebuild the index PK_DEPS | DBA | Solution team | Venkata | 2015-08-21 | 10:00 | 2015-08-21 | 20:00 | 10:00
#REF! |  | Rebuild the index DEPS_I3 | DBA | Solution team | Venkata | 2015-08-21 | 10:00 | 2015-08-21 | 20:00 | 10:00
#REF! |  | Rebuld the index PK_GROUPS | DBA | Solution team | Venkata | 2015-08-21 | 10:00 | 2015-08-21 | 20:00 | 10:00
#REF! |  | Rebuild the index ITEM_MASTER_I3 | DBA | Solution team | Venkata | 2015-08-21 | 10:00 | 2015-08-21 | 20:00 | 10:00
#REF! |  | Rebuild the index PK_ITEM_MASTER | DBA | Solution team | Venkata | 2015-08-21 | 10:00 | 2015-08-21 | 20:00 | 10:00
#REF! |  | Rebuild the index ORDLOC_REV_I1 | DBA | Solution team | Venkata | 2015-08-21 | 10:00 | 2015-08-21 | 20:00 | 10:00
#REF! |  | Rebuild the index ORDLOC_REV_I2 | DBA | Solution team | Venkata | 2015-08-21 | 10:00 | 2015-08-21 | 20:00 | 10:00
#REF! |  | Rebuild the index PK_ORDLOC_REV ( | DBA | Solution team | Venkata | 2015-08-21 | 10:00 | 2015-08-21 | 20:00 | 10:00
#REF! |  | Check for any Invalid object? select * from all_objects where status <> 'VALID' and owner = 'RMSAPPS'; | DBA | Solution team | Venkata | 2015-08-21 | 10:00 | 2015-08-21 | 20:00 | 10:00
#REF! |  | Recompile all object to get rid off Invalid objects | DBA | Solution team | Venkata | 2015-08-21 | 10:00 | 2015-08-21 | 20:00 | 10:00
#REF! | Allocation Patch Upgrade |  | DBA | Solution team | Venkata | 2015-08-21 | 10:00 | 2015-08-21 | 20:00 | 10:00
#REF! |  | Take a back up of all components | DBA | Solution team | Venkata | 2015-08-21 | 10:00 | 2015-08-21 | 20:00 | 10:00
#REF! |  | DB script upgrade | DBA | Solution team | Venkata | 2015-08-21 | 10:00 | 2015-08-21 | 20:00 | 10:00
#REF! |  | Check for any Invalid object? select * from all_objects where status <> 'VALID' and owner = 'RMSAPPS'; | DBA | Solution team | Venkata | 2015-08-21 | 10:00 | 2015-08-21 | 20:00 | 10:00
#REF! |  | Recompile all object to get rid off Invalid objects | DBA | Solution team | Venkata | 2015-08-21 | 10:00 | 2015-08-21 | 20:00 | 10:00
#REF! | Application upgrade | RMS Application Upgrade to 13.2.8 | DBA | Solution team | Venkata | 2015-08-21 | 10:00 | 2015-08-21 | 20:00 | 10:00
#REF! |  | Forms upgrade - | DBA | Solution team | Venkata | 2015-08-21 | 9:00 | 2015-08-21 | 20:00 | 11:00
#REF! |  | Replenishment Policy Maintenance form change ( Make sure not to deploy in PROD unless reported) | DBA | Solution team | Venkata | 2015-08-21 | 9:00 | 2015-08-21 | 20:00 | 11:00
#REF! |  | Compile all the Forms. No error should be seen | DBA | Solution team | Venkata | 2015-08-21 | 9:00 | 2015-08-21 | 20:00 | 11:00
#REF! |  | Pro*c / KSh upgrade | DBA | Solution team | Venkata | 2015-08-21 | 9:00 | 2015-08-21 | 20:00 | 11:00
#REF! |  | Compile all Pro*c | DBA | Solution team | Venkata | 2015-08-21 | 9:00 | 2015-08-21 | 20:00 | 11:00
#REF! |  | RIB Application Upgrade to 13.2.8 | DBA | Solution team | Venkata | 2015-08-21 | 9:00 | 2015-08-21 | 20:00 | 11:00
#REF! | RPM Java Version | Make sure RPM Server level java is set properly to java 1.7 | DBA | Solution team | Venkata | 2015-08-21 | 9:00 | 2015-08-21 | 20:00 | 11:00
#REF! | ReIM Java Version | Make sure ReIM Server level java is set properly to java 1.7  Java: JDK 1.7.0+ 64 bit | DBA | Solution team | Venkata | 2015-08-21 | 9:00 | 2015-08-21 | 20:00 | 11:00
#REF! |  | RPM application upgrade to 13.2.8 | DBA | Solution team | Venkata | 2015-08-21 | 9:00 | 2015-08-21 | 20:00 | 11:00
#REF! |  | ReIM application Upgrade to 13.2.8 | DBA | Solution team | Venkata | 2015-08-21 | 9:00 | 2015-08-21 | 20:00 | 11:00
#REF! | Allocation Patch availability |  | DBA | Solution team | Venkata | 2015-08-21 | 9:00 | 2015-08-21 | 20:00 | 11:00
#REF! |  | Application upgrade to 13.3.1 | DBA | Solution team | Venkata | 2015-08-21 | 9:00 | 2015-08-21 | 20:00 | 11:00
#REF! |  | Allocation upgrade 13.3.1 completion | DBA | Solution team | Venkata | 2015-08-21 | 9:00 | 2015-08-21 | 20:00 | 11:00
#REF! | Retrofit For Upgrade
#REF! |  | RMS_13.2.8 Upgrade_Foundation Changes | DBA | Solution team | Venkata | 2015-08-23 | 9:00 | 2015-08-23 | 20:00 | 11:00
#REF! |  | RMS_13.2.8 Upgrade_Foundation_DC_Load | DBA | Solution team | Venkata | 2015-08-23 | 9:00 | 2015-08-23 | 20:00 | 11:00
#REF! |  | RMS_13.2.8 Upgrade_PO_Changes | DBA | Solution team | Venkata | 2015-08-23 | 9:00 | 2015-08-23 | 20:00 | 11:00
#REF! |  | RMS_13.2.8_Upgrade_Inventory_StockLedger Changes | DBA | Solution team | Venkata | 2015-08-23 | 9:00 | 2015-08-23 | 20:00 | 11:00
#REF! |  | RMS_13.2.8_Upgrade_INV_SL_Extension_changes | DBA | Solution team | Venkata | 2015-08-23 | 9:00 | 2015-08-23 | 20:00 | 11:00
#REF! |  | RMS_Upgrade_HotFix_20715149_RUA | DBA | Solution team | Venkata | 2015-08-23 | 9:00 | 2015-08-23 | 20:00 | 11:00
#REF! |  | RMS_Foundation_Hotfix21157777_Mass_Cost_Updates | DBA | Solution team | Venkata | 2015-08-23 | 9:00 | 2015-08-23 | 20:00 | 11:00
#REF! |  | RMS_13.2.8_Upgrade_V_Shipment | DBA | Solution team | Venkata | 2015-08-23 | 9:00 | 2015-08-23 | 20:00 | 11:00
#REF! |  | RMS_13.2.8_REPL_POLICY_LOV_Performance_fix - 000940 | DBA | Solution team | Venkata | 2015-08-23 | 9:00 | 2015-08-23 | 20:00 | 11:00
#REF! |  | RMS_13.2.8 ORDLOC Performance Fix - 000926 | DBA | Solution team | Venkata | 2015-08-23 | 9:00 | 2015-08-23 | 20:00 | 11:00
#REF! |  | RMS_Upgrade_prcimp - 000923 | DBA | Solution team | Venkata | 2015-08-23 | 9:00 | 2015-08-23 | 20:00 | 11:00
#REF! |  | RMS_13.2.8 Upgrade EDI Alternate Fix - 000925 | DBA | Solution team | Venkata | 2015-08-23 | 9:00 | 2015-08-23 | 20:00 | 11:00
#REF! |  | RMS_13.2.8_Upgrade_REQEXT_Wrapper_Fix | DBA | Solution team | Venkata | 2015-08-23 | 9:00 | 2015-08-23 | 20:00 | 11:00
#REF! |  | RMS_13.2.8 Upgrade Custom Delayed alloc Fix - 000921 | DBA | Solution team | Venkata | 2015-08-23 | 9:00 | 2015-08-23 | 20:00 | 11:00
#REF! |  | RIB_Upgrade 13.2.8 - RIB CONFIG CHANGES FOR MULTI THREADING - The CHANGES Already part of the RMS Foundation Retorifit | DBA | Solution team | Venkata | 2015-08-23 | 9:00 | 2015-08-23 | 20:00 | 11:00
#REF! |  | Make sure the Multithread is deployed | DBA | Solution team | Venkata | 2015-08-23 | 9:00 | 2015-08-23 | 20:00 | 11:00
#REF! |  | RPM_13.2.8 Upgrade_changes | DBA | Solution team | Venkata | 2015-08-23 | 9:00 | 2015-08-23 | 20:00 | 11:00
#REF! |  | ReIM_13.2.8_Upgrade Changes | DBA | Solution team | Venkata | 2015-08-23 | 9:00 | 2015-08-23 | 20:00 | 11:00
#REF! |  | ReIM_13.2.8_Base_And_AutoMatch_Hotfix | DBA | Solution team | Venkata | 2015-08-23 | 9:00 | 2015-08-23 | 20:00 | 11:00
#REF! |  | ReIM_13.2.8_Hotfix_Check_With_Debug | DBA | Solution team | Venkata | 2015-08-23 | 9:00 | 2015-08-23 | 20:00 | 11:00
#REF! |  | REIM_13.2.8_Upgrade_Bugfix_19954952_20806217 | DBA | Solution team | Venkata | 2015-08-23 | 9:00 | 2015-08-23 | 20:00 | 11:00
#REF! |  | REIM_13.2.8_Upgrade_Bugfix_19630875_20008917 | DBA | Solution team | Venkata | 2015-08-23 | 9:00 | 2015-08-23 | 20:00 | 11:00
#REF! | ReIM.Properties | Update the ReIM. Properties value ( compare with the value what it should be) | DBA | Solution team | Venkata | 2015-08-23 | 9:00 | 2015-08-23 | 20:00 | 11:00
#REF! |  | pool.connectionWaitTimeout=5 | DBA | Solution team | Venkata | 2015-08-23 | 9:00 | 2015-08-23 | 20:00 | 11:00
#REF! |  | pool.propertyCheckInterval=60 | DBA | Solution team | Venkata | 2015-08-23 | 9:00 | 2015-08-23 | 20:00 | 11:00
#REF! |  | pool.timeToLiveTimeout=0 | DBA | Solution team | Venkata | 2015-08-23 | 9:00 | 2015-08-23 | 20:00 | 11:00
#REF! |  | pool.inactivityTimeout=600 | DBA | Solution team | Venkata | 2015-08-23 | 9:00 | 2015-08-23 | 20:00 | 11:00
#REF! |  | pool.abandonedConnectionTimeout=0 | DBA | Solution team | Venkata | 2015-08-23 | 9:00 | 2015-08-23 | 20:00 | 11:00
#REF! |  | edi.upload.multithreaded=TRUE | DBA | Solution team | Venkata | 2015-08-23 | 9:00 | 2015-08-23 | 20:00 | 11:00
#REF! |  | thread.backgroundThreadTimeout=1800000 | DBA | Solution team | Venkata | 2015-08-23 | 9:00 | 2015-08-23 | 20:00 | 11:00
#REF! |  | thread.consumerThreadTimeout=600000 | DBA | Solution team | Venkata | 2015-08-23 | 9:00 | 2015-08-23 | 20:00 | 11:00
#REF! |  | thread.consumerThreadKeepAlive=0 | DBA | Solution team | Venkata | 2015-08-23 | 9:00 | 2015-08-23 | 20:00 | 11:00
#REF! |  | always.show.suppliersite=true | DBA | Solution team | Venkata | 2015-08-23 | 9:00 | 2015-08-23 | 20:00 | 11:00
#REF! |  | INCLUDE_DOC_DATE_FOR_DUPLICATE_DOC_CHECK = true | DBA | Solution team | Venkata | 2015-08-23 | 9:00 | 2015-08-23 | 20:00 | 11:00
#REF! |  | INCLUDE_DOC_DATE_FOR_DUPLICATE_YEAR_CHECK = true | DBA | Solution team | Venkata | 2015-08-23 | 9:00 | 2015-08-23 | 20:00 | 11:00
#REF! |  | thread.invoiceautomatchbatch.thread.threshold=20 | DBA | Solution team | Venkata | 2015-08-23 | 9:00 | 2015-08-23 | 20:00 | 11:00
#REF! |  | void_late_credit_note_requests=true | DBA | Solution team | Venkata | 2015-08-23 | 9:00 | 2015-08-23 | 20:00 | 11:00
#REF! |  | Exchange_rate_type =USER | DBA | Solution team | Venkata | 2015-08-23 | 9:00 | 2015-08-23 | 20:00 | 11:00
#REF! |  | document.number.validatation.regexpr=^[0-9A-Z#a-z\ \+\-\_\\p{Punct}]+$ | DBA | Solution team | Venkata | 2015-08-23 | 9:00 | 2015-08-23 | 20:00 | 11:00
#REF! |  | intra_region_post_ind = true | DBA | Solution team | Venkata | 2015-08-23 | 9:00 | 2015-08-23 | 20:00 | 11:00
#REF! |  | im.qty.review.records.maximum= | DBA | Solution team | Venkata | 2015-08-23 | 9:00 | 2015-08-23 | 20:00 | 11:00
#REF! | System.properties |  | DBA | Solution team | Venkata | 2015-08-23 | 9:00 | 2015-08-23 | 20:00 | 11:00
#REF! |  | system.gl_option_dynamic_1=N | DBA | Solution team | Venkata | 2015-08-23 | 9:00 | 2015-08-23 | 20:00 | 11:00
#REF! |  | system.gl_option_dynamic_2=Y | DBA | Solution team | Venkata | 2015-08-23 | 9:00 | 2015-08-23 | 20:00 | 11:00
#REF! |  | system.gl_option_dynamic_3=N | DBA | Solution team | Venkata | 2015-08-23 | 9:00 | 2015-08-23 | 20:00 | 11:00
#REF! |  | system.gl_option_dynamic_4=N | DBA | Solution team | Venkata | 2015-08-23 | 9:00 | 2015-08-23 | 20:00 | 11:00
#REF! |  | system.gl_option_dynamic_5=N | DBA | Solution team | Venkata | 2015-08-23 | 9:00 | 2015-08-23 | 20:00 | 11:00
#REF! |  | system.gl_option_dynamic_6=N | DBA | Solution team | Venkata | 2015-08-23 | 9:00 | 2015-08-23 | 20:00 | 11:00
#REF! |  | system.gl_option_dynamic_7=N | DBA | Solution team | Venkata | 2015-08-23 | 9:00 | 2015-08-23 | 20:00 | 11:00
#REF! |  | system.gl_option_dynamic_8=N | DBA | Solution team | Venkata | 2015-08-23 | 9:00 | 2015-08-23 | 20:00 | 11:00
#REF! |  | system.gl_option_dynamic_9=N | DBA | Solution team | Venkata | 2015-08-23 | 9:00 | 2015-08-23 | 20:00 | 11:00
#REF! |  | system.gl_option_dynamic_10=N | DBA | Solution team | Venkata | 2015-08-23 | 9:00 | 2015-08-23 | 20:00 | 11:00
#REF! |  | system.gl_option_dynamic_11=N | DBA | Solution team | Venkata | 2015-08-23 | 9:00 | 2015-08-23 | 20:00 | 11:00
#REF! |  | system.gl_option_dynamic_12=N | DBA | Solution team | Venkata | 2015-08-23 | 9:00 | 2015-08-23 | 20:00 | 11:00
#REF! |  | system.gl_option_dynamic_13=N | DBA | Solution team | Venkata | 2015-08-23 | 9:00 | 2015-08-23 | 20:00 | 11:00
#REF! |  | system.gl_option_dynamic_14=N | DBA | Solution team | Venkata | 2015-08-23 | 9:00 | 2015-08-23 | 20:00 | 11:00
#REF! |  | system.gl_option_dynamic_mapping_2=LOCATION | DBA | Solution team | Venkata | 2015-08-23 | 9:00 | 2015-08-23 | 20:00 | 11:00
#REF! |  | CRDNRT=CNRVT | DBA | Solution team | Venkata | 2015-08-23 | 9:00 | 2015-08-23 | 20:00 | 11:00
#REF! | ReimResources.properties |  | DBA | Solution team | Venkata | 2015-08-23 | 9:00 | 2015-08-23 | 20:00 | 11:00
#REF! |  | label.sys_opt_Prorate_Across_Tax_Codes=Prorate Across Tax Codes | DBA | Solution team | Venkata | 2015-08-23 | 9:00 | 2015-08-23 | 20:00 | 11:00
#REF! | Struts-config.xml |  | DBA | Solution team | Venkata | 2015-08-23 | 9:00 | 2015-08-23 | 20:00 | 11:00
#REF! |  | <action path="/invoiceAdvancedSearchResultFormLinkAction" type="com.retek.reim.ui.invoiceMaintenance.InvoiceAdvancedSearchResultFormLinkAction" name="invoiceAdvSearchResultForm" scope="session"> <forward name="failure" path="/invoice_search_result.jsp" /> <forward name="success" path="/documentMaintenanceHeaderView.do" /> <forward name="unauthorized_access" path="/home.do?targetTab=t4" /> </action> | DBA | Solution team | Venkata | 2015-08-23 | 9:00 | 2015-08-23 | 20:00 | 11:00
#REF! | Post Deployment Activities | Validation:
#REF! |  | RIB - Multi threadinging Deployed | DBA | Solution team | Venkata | 2015-08-23 | 9:00 | 2015-08-23 | 20:00 | 11:00
#REF! |  | New custom trigger on item_master - BELK_ITMPRG_IEM_ADR – need to verify as part of Post Upgrade deployment verification that this trigger still exists on PROD. | DBA | Solution team | Venkata | 2015-08-23 | 9:00 | 2015-08-23 | 20:00 | 11:00
#REF! |  | Change to Initrans on base tables - item_mfqueue, uda_item_ff, item_country, ITEM_SUPP_MANU_COUNTRY, ITEM_SUPPLIER_CFA_EXT & DAILY_PURGE – need to verify as part of Post Upgrade deployment verification that the initrans changes ( table lebel to 6 and index level to 12) | DBA | Solution team | Venkata | 2015-08-23 | 9:00 | 2015-08-23 | 20:00 | 11:00
#REF! |  | Changes to make files - rms.mk & rms_include.mk - This has impact on Upgrade changes. While migrating to STG/PROD, DEV team need to make sure to merge the latest make file from STG (having new PRO*C entries) to the upgrade/retrofitted version of make file. | DBA | Solution team | Venkata | 2015-08-23 | 9:00 | 2015-08-23 | 20:00 | 11:00
#REF! |  | restart table entries - need to verify as part of Post Upgrade deployment verification that entry of new batch – belkitmprg still exists in restart_control & restart_program_status tables. | DBA | Solution team | Venkata | 2015-08-23 | 9:00 | 2015-08-23 | 20:00 | 11:00
#REF! | Memory Issue | ReIM heap size param set up : 8 Gigs The memory setting for reim servers have to be set correctly to have 8gig. | DBA | Solution team | Venkata | 2015-08-23 | 9:00 | 2015-08-23 | 20:00 | 11:00
215 | RPM new Item location | Multi Threading | DBA | Solution team
216 | RIB | Confirm new index on item_master on deposit_item_type | DBA | Solution team
Formulas:
End Date = [Start Date]
End Date = [End Date, row above]
Start Date = [End Date, row above]
Start Date = [Start Date, row above]

## Contact List
Team | Team Member | On site/Remote | Email / Mobile Number
drive | Subba | On Site | 512-947-7979
CARS | Santosh | On Site | 425-223-8886
CARS | Laura | Backup

## Deployment Tasks
No | Program | Task | Responsible Team | Accountable Resource | Supporting Resource | Start Date | Est Start Time | End Date | Est End Time | Status
1 | Pre-deployment Activities | Create change Ticket for deployment | CARS |  |  | 2016-11-29 | 10:00 | 16:00 |  | Not Started
2 |  | Take copy of the production build for CARS UI, PROD JOB and VIP JOBS | CARS |  |  | 2016-11-29 | 10:00 | 16:00 |  | Not Started
3 | Deployment Activities | Bring down the cars UI & prod, vip application server Server : 40.143.11.3 Script location for CARS Prod/VIP Job servers.: ./cars/stopCarsProdJobs.sh ./cars/stopCarsVIPJobs.sh | CARS, Support |  |  | 2016-11-30 | 18:10 | 18:20 |  | Not Started
4 |  | Bring down CARS web server (40.143.9.2) sudo /usr/sbin/httpd -f /var/cars/cars/httpdprod/conf/httpd-cars-prod.conf -k stop | CARS, Support |  |  | 2016-11-30 | 18:20 | 18:30 |  | Not Started
5 |  | Take back up of current prod ui, Jobs build ( for proddcution prod ui, VIP job & prod jobs) -take the Backup of existing cars folder on CARS production server Location:/cars/TOMCAT_PROD_JOBS/webapps/ and /cars/TOMCAT_UI_2/webapps Backup location: /cars/bakckup/TOMCAT_UI_1/cars_backup_113016/ and /cars/bakckup/TOMCAT_UI_2/cars_backup_113016/ (CARS_BACKUP_MM_DD_YYYY_HH_MM_SS) for CARS UI instances. DO NOT CREATE BACKUPS IN /cars/TOMCAT_PROD_JOBS or /cars/TOMCAT_UI_2 directories! | CARS, Support |  |  | 2016-11-30 | 18:30 | 18:45 |  | Not Started
6 |  | Download the appropriate version from nexus for each of the CARS war files. Nexus url: http://belkecaral103:8081/nexus/content/repositories/releases/com/belk/belk-ec-cars-application/ belk-ec-cars-application-1.0.1.235-prod-ui.war belk-ec-cars-application-1.0.1.236-prod-jobs.war belk-ec-cars-application-1.0.1.237-prod-vip-jobs.war | CARS, Support |  |  | 2016-12-01 | 18:30 | 18:45 |  | Not Started
7 |  | Copy the appropriate applicationContext-resources.xml directly into its corresponding WAR file. Source (on shared drive): G:\Ecommerce\releases\r27_xenogears.8\config_for_prod-jobs\ G:\Ecommerce\releases\r27_xenogears.8\config_for_prod-ui\ G:\Ecommerce\releases\r27_xenogears.8\config_for_prod-vip-jobs\ Destination (within WAR file): /cars/WEB-INF/classes/ | CARS, Support |  |  | 2016-12-01 | 18:45 | 18:50 |  | Not Started
8 |  | Deploy prod build for prodution prod ui, VIP job & prod jobs -Deploy the appropriate version from nexus for each of these wars. | CARS, Support |  |  | 2016-11-30 | 18:50 | 19:30 |  | Not Started
9 |  | Bring up the CARS application server - prod Server : 40.143.11.2 . /restartCARSUI1.sh . /restartCARSUI2.sh Server : 40.143.11.3 ./restartProdJobs.sh ./restartVIPJobs.sh | CARS, Support |  |  | 2016-11-30 | 19:30 | 19:40 |  | Not Started
10 |  | Check if the startup process for the server succeeded. Log file location for CARS UI/Batch Jobs: /cars/<server>logs | CARS, Support |  |  | 2016-11-30 | 19:40 | 19:45 |  | Not Started
11 |  | Start cars webserver(40.143.9.2) sudo /usr/sbin/httpd -f /var/cars/cars/httpdprod/conf/httpd-cars-prod.conf -k start | CARS, Support |  |  | 2016-11-30 | 19:45 | 19:50 |  | Not Started
12 |  | Run manully job, which is stoped the time between XXXX to XXXX | CARS, Support |  |  | 2016-11-30 | 19:50 | 20:00 |  | Not Started
13 |  | Carry out smoke test on CARs application by login with carsadmin@belk.com on url :https://cars.belk.com/signin.html | CARS , QE |  |  | 2016-11-30 | 20:00 | onwards |  | Not Started
14 |  | Run the CARS job manully in sequence, which is held during the deployment | Support |  |  | 2016-11-30 | 20:00 | 20:30 |  | Not Started
15 | Post Deployment Activities | Moniter the all the jobs | CARS, Support |  |  | 2016-11-30 | 20:00 | onwards |  | Not Started
16 |  | moniter the cars log | CARS, Support |  |  | 2016-11-30 | 20:00 | onwards |  | Not Started
17 |  | Send business communication for deployment completes | CARS, Support |  |  | 2016-11-30 | 20:00 | onwards |  | Not Started

## Backout plan
Sr.No | Activity | Start Time | Estimated end Time | Assigned | Status
CARS BACKOUT
1 | Send the communication email to all stakeholders informing backout activity in CARS application | 0:00 |  | Ravi K | Not Started
2 | Stop the CARS UI applications servers:/cars folder Server : 40.143.11.2 Script location for CARS UI1/UI2 Appl.: ./stopCarsUI1.sh ./stopCarsUI2.sh |  |  | CARS/SUPPORT | Not Started
3 | Stop cars webserver(40.143.9.2) sudo /usr/sbin/httpd -f /var/cars/cars/httpdprod/conf/httpd-cars-prod.conf -k stop |  |  | CARS/SUPPORT | Not Started
4 | Remove all the DB changes - (DB remove script will be incoprated) |  |  | DBA | Not Started
5 | Ensure non of the CARS PROD /VIP job running then Stop the CARS Batch Server "/cars/ folder Server : 40.143.11.3 Stop Script.: ./stopCarsProdJobs.sh ./stopCarsVIPJobs.sh |  |  | CARS/SUPPORT | Not Started
6 | remove the latest deployed war file and redeploy the backup file Note : get the beckup path in deployment section |  |  | CARS/SUPPORT | Not Started
7 | start the CARS UI and Job Servers folder :/cars Server : 40.143.11.2 . /restartCARSUI1.sh . /restartCARSUI2.sh Server : 40.143.11.3 ./restartProdJobs.sh ./restartVIPJobs.sh |  |  | CARS/SUPPORT | Not Started
8 | Check if the startup process for the server succeeded. Log file location for CARS UI: /cars/<SERVERS>/catelina.out |  |  | CARS/SUPPORT | Not Started
9 | Run manully job, which needs to run between XXXX to XXXX(Support tema has list of job ) |  |  | CARS/SUPPORT | Not Started
10 | Start cars webserver(40.143.9.2) sudo /usr/sbin/httpd -f /var/cars/cars/httpdprod/conf/httpd-cars-prod.conf -k start |  |  | CARS/SUPPORT | Not Started
11 | Carry out smoke test on CARs application by login with carsadmin@belk.com on url :https://cars.belk.com/signin.html |  |  | QE | Not Started
12 | Send the post deployment communication email to all stakeholders |  |  | Ravi K | Not Started
13 | Monitor the Server log files |  |  | CARS/SUPPORT | Not Started

## CMP Deployment (hidden)
No | Program | Task | Responsible Team | Accountable Resource | Supporting Resource | Start Date | Est Start Time | End Date | Est End Time | Status
| Pre-deployment Activities | Send email comunication to buisness | CARS |  |  | 2016-03-01 | 10:00 | 16:00
|  | Keep all the class files ready (compiled with JDK1.4) | CARS |  |  | 2016-03-01 | 10:00 | 16:00
|  | Keep all thejob script ready | CARS |  |  | 2016-03-01 | 10:00 | 16:00
|  | Keep all the DB scripts are ready | CARS |  |  | 2016-03-01 | 10:00 | 16:00
| Deployment Activities | Bring Down CMP server (40.143.11.5) Path: /www/a/bmcesp/ ./stopJMS.sh ./stopEAC.sh ./stopED.sh ./stopCMP.sh | SUPPORT |  |  | 2016-03-03 | 19:00 | 19:10
|  | \\belkfs2\MIS\Ecommerce\CARS_RELEASE\PIM_INTEGRATION\CMP\classes\CESProcessPIMAttributeUpdates.clss Depoly the class file in /www/a/bmcesp/core/classes/com/belk/ces/ | SUPPORT |  |  | 2016-03-03 | 19:10 | 19:30
|  | Deploy the Script files copy \\belkfs2\MIS\Ecommerce\CARS_RELEASE\PIM_INTEGRATION\CMP\scripts\process_pim_attribute_data.sh to /www/a/bmcesp/ copy \\belkfs2\MIS\Ecommerce\CARS_RELEASE\PIM_INTEGRATION\CMP\scripts\ load_pim_attribute_data.ctl to /www/a/bmcesp/interface_load/pim_attribute_update/sqlloader/load_pim_attribute_data.ctl | SUPPORT |  |  | 2016-03-03 | 19:30 | 19:35
|  | Execute the DB script \\belkfs2\MIS\Ecommerce\CARS_RELEASE\PIM_INTEGRATION\DBSCRIPTS\cmp_cutover\Pkg_Process_PIM_Attribute.sql into ces@belkcesp DB | SUPPORT |  |  | 2016-03-03 | 19:35 | 19:45
|  | Add the cron job :00 03 * * * /www/a/bmcesp/process_pim_attribute_data.sh>> /www/a/bmcesp/logprocess_pim_attribute_data/process_pim_attribute_data-`date +\%m\%d\%H\%M`.log | SUPPORT |  |  | 2016-03-03 | 19:45 | 19:50
|  | Bring up CMP application server (40.143.11.5) Path: /www/a/bmcesp/ ./startJMS.sh ./startEAC.sh ./startED.sh ./startCMP.sh | SUPPORT |  |  | 2016-03-03 | 19:45 | 20:00
|  | QA to start smoke testing (http://cmp.belkinc.com:7577/contact/login.jsp) | CARS/QE |  |  | 3/3/2016 to 5/05/2016 | 22:30 | onwards
|  | Ensure all the CMP jobs are running as expected | CARS/SUPPORT |  |  | 3/3/2016 to 5/05/2016 | 22:30 | onwards
| Post Deployment Activities | Validate all the CMP jobs and logs | CARS |  |  | 3/3/2016 to 5/05/2016 | 22:30 | onwards
|  | Moniter the all the jobs | CARS, Support |  |  | 3/3/2016 to 5/05/2016 | 22:30 | onwards
| Deployment Closeout Activities | Send business communication for deployment completes | Vasanth |  |  | 2016-03-05

## CMP Backout (hidden)
Sr.No | Activity | Start Time | Estimated end Time | Assigned | Status
CMP BACKOUT
1 | Send the communication email to all stakeholders informing backout activity in CARS application | 2016-03-05 |  | Vasanth | Not Started
2 | Bring Down CMP server (40.143.11.5) Path: /www/a/bmcesp/ ./stopJMS.sh ./stopEAC.sh ./stopED.sh ./stopCMP.sh | 2016-03-05 |  | SUPPORT | Not Started
3 | Revert the class file : Depoly the class file in /www/a/bmcesp/core/classes/com/belk/ces/CESProcessPIMAttributeUpdates.clss | 2016-03-05 |  | SUPPORT | Not Started
4 | Revert the DB procedure Pkg_Process_PIM_Attribute.sql into ces@belkcesp DB | 2016-03-05 |  | DBA | Not Started
5 | Remove the cron job and shell script 00 03 * * * /www/a/bmcesp/process_pim_attribute_data.sh>> /www/a/bmcesp/logprocess_pim_attribute_data/process_pim_attribute_data-`date +\%m\%d\%H\%M`.log | 2016-03-05 |  | SUPPORT | Not Started
6 | Bring up CMP application server (40.143.11.5) Path: /www/a/bmcesp/ ./startJMS.sh ./startEAC.sh ./startED.sh ./startCMP.sh | 2016-03-05 |  | SUPPORT | Not Started
7 | QA to start smoke testing (http://cmp.belkinc.com:7577/contact/login.jsp) | 2016-03-05 |  | CARS/QE | Not Started
8 | Ensure all the CMP jobs are running as expected | 2016-03-05 |  | CARS/SUPPORT | Not Started
9 | Send the communication email to all stakeholders informing backout activity in CMP application | 2016-03-05 |  | Vasanth | Not Started
10 | Moniter CMP logs | 2016-03-05 |  | SUPPORT/CARS | Not Started

## CARS JOB (hidden)
Sr No | Job Name | Job Description | If Job Fails? | Job Run time/Start time | Tomcat Instance
1 | Import Vendor Catalog Data | Loads CARS DB with Style details from a spreadsheet uploaded by CARS users. | Users can not complete the drop ship CARS | 12:00 | TOMCAT_PROD_JOB
2 | Copy Avail To Tmp | Copy SKU inventory from BEL_INV_AVAIL table to temporary table TMP_SKU_AVAIL for reporting purposes (CARS To CMP Status Report) | CARSTOCMP Reports cannot be generated by cars Users. | 14:00 | TOMCAT_PROD_JOB
3 | Import Dropship CARs | Processes feed received from mainframe (WIC40000 job) which contains details of styles/SKUs set as 'DROPSHIP' in IDB and generates CARs. | Dropship cars will not be generated | 20:00 | TOMCAT_PROD_JOB
4 | Vendor Image Transfer Job | Transfers all the vendor image files stored in belkmacl to RRD FTP | Images cannot be validated(Pass/Fail) in cars application | 8:00 PM to 9:30 PM | Root
5 | Export Manual CARs | Generates a .txt file with all manual CARs requested by users in the application. | WIC70000 job won't be able to generate mcar.txt and car.txt feed files for CARS. | 21:00 | TOMCAT_PROD_JOB
6 | Export Vendor Images Update feed | Generates an .xml file containing the details of vendor images which were REMOVED on that day and which had passed MQ and transfers the file to RRD FTP | Vendor images on media compass won't be deleted and the images which are uploaded by vendor won't be availble for Art director creative check. | 21:00 | TOMCAT_VIP_JOB
7 | Unlock All CARs | Unlocks all CARs which are locked by users while editing during the day. | CARS which are locked for editing, won't be unlocked. | 21:30 | TOMCAT_PROD_JOB
8 | Export Vendor Images feed for mechanical check | Generates an .xml file containing the details of vendor images which were uploaded during that day and sends the file to RRD FTP for MQ check; also deletes the vendor images from belkmacl which have been transferred to RRD FTP | Image will not be vaildated where buyer will not able to approve the image. | 22:00 | TOMCAT_VIP_JOB
9 | Export RRD Feeds | Export a .xml feed file to RRD for list of images requested from RRD. | RRD won't be able process the sample images. | 22:15 | TOMCAT_PROD_JOB
10 | Send Vendor Sample Escalation List | Sends emails to the vendor prior to three days of ‘Due date’ if any CARs sample(s) are still in ‘requested’ status | Buyer will not be aware of the sample uploaded by the vendor | 22:30 | TOMCAT_PROD_JOB
11 | Send Vendor CAR Escalation List | Sends emails to the vendor(s) on car escalation date if the car is still assigned to vendor | Corresponding cars will be moved to LatecarsGroup Section. | 23:00 | TOMCAT_PROD_JOB
12 | Import Vendor Images history feed | Processes the xml feed from RRD for all vendor images which have been completed in MediaCompass at RRD; these will be marked as received in CARS after processing | Buyer will not be able to approve the image uploaded by user | 23:00 | TOMCAT_VIP_JOB
13 | Send Late CAR Report | Send email report for Late CARs in "Buyer" status and "Vendor" status to Web merchants, DMM and GMM. | Business users won't be aware of the Late CAR details. | 11:10 PM (Sunday) | TOMCAT_PROD_JOB
14 | Import Vendor Catalog Data | Loads CARS DB with Style details from a spreadsheet uploaded by CARS users after which catalog is ready for data mapping between CARS attributes and Vendor provided attributes (Catalog). | Dropship CARS which are supposed to complete will be delayed. | 23:15 | TOMCAT_PROD_JOB
15 | Import RLR Info | Processes the feed received from mainframe (WIC54050 job). | Whatever the changes that happens in RLR System (Departemnt and classification Changes) will not be Updated to Cars System | 23:30 | TOMCAT_PROD_JOB
16 | Import RRD Feeds | Imports a .xml feed file from RRD and processes it for loading CARs with the received images. | Images in CARS won't be marked as Received and untill CARS marked as Received... Information to CMP won't be sent. | 23:59 | TOMCAT_PROD_JOB
17 | Import MC Image Feed | Import and process .xml feed file from RRD for loading CARs with temporarys images; inserts all MQ_PASSED vendor images for the previous day and generates a temporary image URL in MEDIA_COMPASS_IMAGE table | The CARS waiting for temporary image link won't be sent to CMP. | 0:15 | TOMCAT_PROD_JOB
18 | Load MC Image | Load Media Compass temporary images from RRD to belkmacl for images processed by Import MC Image feed job | The temporary image link url won't be available for sending it to CMP. | 0:45 | TOMCAT_PROD_JOB
19 | Import CARs | Processes the PO CAR and manual CAR feeds received from mainframe (WIC70000 job). | Cars will not be generated | 1:00 AM to 4:00 AM (Every 15 min) | TOMCAT_PROD_JOB
20 | Resynch Size Values Of VendorSkus | Resyncs size names of new/existing SKUs based on the size rules created by the CARS users. | Size won't be converted as per Belk Standards. | Invoked upon Import CARS job completion | TOMCAT_PROD_JOB
21 | Export CES Info | Generates and exports a .xml file which contains the details of all CARs that have been sent to CMP. | CARS information will not be updated in CMP which have been sent to CMP. | 1:25 | TOMCAT_PROD_JOB
22 | Import Vendor Image Mechanical & Creative check XML | Processes the .xml feed from RRD which is a response for the vendor images sent for MQ; vendor images will be marked as MQ_PASSED or MQ_FAILED based on the response | Image Status will retain the same where Buyer cannot approve the images. | 2:00 AM & 5:00 AM | TOMCAT_VIP_JOB
23 | Import User Rank data | Import userrank data feed from mainframe | Failed to get latest DMM/GMM information | 4:00 | TOMCAT_PROD_JOB
24 | Export Products In Trend | Export fashion trends BlueMartini attributes to CMP |  | 4:45 | TOMCAT_PROD_JOB
25 | Send User Notification | Sends notifications to CARS users when a new CAR is generated and/or assigned respectively. | User won't be aware of any new CAR, if it got generated for him. | 5:00 | TOMCAT_PROD_JOB
26 | Load Vendor Catalog Data Into CARS | Gets necessary attributes from an imported catalog to prefill DROPSHIP CARs. | Catalogs uploaded into CARS will not be processed | 5:15 | TOMCAT_PROD_JOB
27 | Send Vendor Notification | Sends notifications to"Vendor" when a new CAR is generated and/or assigned respectively. | User won't be aware of any new CAR, if it got generated for him. | 5:30 | TOMCAT_PROD_JOB
28 | Close CARs | Marks the WORKFLOW STATUS of CARs to 'CLOSED' when all images pending with RRD are received and if the CARs are sent to CMP. | CARS can not be closed and the CARS which supposed to not fall under Late CARS, will fall. | 5:45 | TOMCAT_PROD_JOB
29 | Send Vendor Image Rejection Notification | Sends an email to the configured list of recepients with the details of all MQ_FAILED vendor images | Users can not be aware of the image details which are failed in Mechanical and Creative. | 6:00 | TOMCAT_VIP_JOB
30 | Export Hex Values | This job creates a text file with the color codes and ‘hex’ values of a product and sends it to CMP. |  | 6:15 | TOMCAT_PROD_JOB
31 | Prefill CARs | Prefills DROPSHIP CARs with attributes from processed catalogs. | DATA mapped for vendor catalog can not be processed | 6:45 | TOMCAT_PROD_JOB
32 | Export Vendor Expedited Shipping | Generates a .bmi file with details of vendor expedited shipping and transfers the feed to BM | Information related to dropship can not be delivered to BM | 11:30 | TOMCAT_PROD_JOB

## CMP JOB (hidden)
Sr No | Job Name | Script Path | Job Description | If Job Fails? | Job Run time/Start time | Sequence Run
1 | Stop CMP | /www/a/bmcesp/stopCMP.sh | CMP application job stop script | CMP application will not stop | 3:30 | Any time
2 | Start CMP | /www/a/bmcesp/startCMP.sh | CMP application job start script | CMP application will not start | 3:35 | Any time
3 | CBT Export | /www/a/intbm901/cbtexport/cbtexport.sh | This job will check for cbtempload.dat file in the location (/www/a/intbm901/cbtexport). If the file is available it will proceed further, otherwise it wont run, The Last Run happened on Dec 30 2012. |  | Every 30 minutes
4 | CBT Full Export | /www/a/intbm901/cbtexport/cbtfullexport.sh | This job will check for cbtfullload.dat file in the location (/www/a/intbm901/cbtexport). If the file is available it will proceed further, otherwise it wont run, The Last Run happened on Dec 30 2012. |  | 2:30 AM (Sunday)
5 | Survey Extract | /www/a/intbm901/belk_data/cst/survey.sh | Extract survey data to send to the mainframe |  | 21:00
6 | Store Export | /www/a/intbm901/belk_data/org/strexport.sh | This is used to update bm_intranet_external/martini@belkint darabse with store info data. I guess we don’t use it anywhere for belk.com. But please confirm with Richard once. |  | 2:00
7 |  | /www/a/bm901/belk_data/ilf/cybersource/autoRun.sh | For pulling PaymentBatchDetailReport from cybersource |  | 11:11
8 | Logs cleanup | /www/a/bm901/webcleanup.pl | Log purge script | Memory will increase on CMP server | 23:00 | Any time
9 | Image Transfer | /www/a/integrationdata/rrd/imageTransfer/startImageTransfer.sh | RRD images to belkmacl server job | Images will get piled up on the FTP server ftp.belk.com and will impact the post-production image process as RRD will not be able to post any more images if the server reaches maximum memory | ON-DEMAND / 8:00 AM to 11 PM
10 | Scene7 URL Indexing | /www/a/bmcesp/run_scene7_feed.sh | Scene 7 image job which uploads image URL in CMP | Scene7 URLs will not be generated for newly generated image tasks | 7:00 AM to 10 PM (Every 15 minutes) | Any time
11 | IDB batch processing | /www/a/bmcesp/run_process_batch.sh | IDB data feed processing job |  | 4:00 | RUN Main frame and run these job
12 | CARS to CMP Import | /www/a/bmcesp/run_cars_feed_new.sh | This job will receive the file (export to CES) from CARS server and it will upload the details into CES database | No new tasks will be created and tasks will not updated in CMP | 1:45 | RUN CARS export job, then run this job
13 | CMP Product Extraction | /www/a/bmcesp/run_cmp_extract.sh | Extracts the latest product details into a BMI and sends to primary server | Approved products will not reach primary website | 5:45 | Run as it is, bluemartini needs to pick this file
14 | IDB to CMP Import | /www/a/bmcesp/interface_load/idb/Merchandise/data/productload.sh | This job will get the Feed from IDB and it will upload the product details of IDB (conversion products) into CES database | Latest products from IDB will not be loaded in CMP | 6:00 AM (Monday)
15 | CARS feed error archiver | /www/a/bmcesp/run_cars_feed_archiver.sh | This job archives any errors during CARS feed processing | Errors in files will not be archived | 7:00 | Enable cron job as it is
16 | Import Bridal SKU info from IDB | /www/a/bmcesp/load_bridal_flag_idb_to_cmp.sh | Loads the bridal SKU information received from IDB in CMP | Latest bridal SKU details will not be available in CMP | 2:59
17 | Category Pattern Extraction | /www/a/bmcesp/interface_load/idb/extract/dw_category_pattern_extract.sh | This job will extract the details from CMP database and creates a .dat file and sends to DWS | DWS system will not get the required file in time | 3:00
18 | Update Set Product Attribute | /www/a/bmcesp/sp_update_sku_product_table.sh | This job will check for Set product and correct the "is_set_brustable" attribute | The "is_set_burstable" attribut will not be updated for newly created set products | 2:00
19 | Copy Crontab | /www/a/bmcesp903/copy_crontab.sh | Takes backup of crontab | Latest Crontab file content will not be available | 5:00
20 | PO Detail Load | /www/a/bmcesp903/interface_load/loadPoDetails/po_details_load.sh | Loads the PO level inventory and price information of SKUs in PO_UNIT_DETAIL table in CARS DB | CARS reports will have old and incorrect data | 2:15
21 | Process CARS facet attributes | /www/a/bmcesp/run_cars_facet_attribute.sh | Loads the facet attributes received from CARS in CMP DB | ON DEMAND script - Not much impact. The latest facet attributes in CARS will not be avaiable in CMP. | ON-DEMAND / 3:00 AM
22 | Logs Cleanup | /www/a/bmcesp903/purge_logs.sh PROD | Log purge script | Memory will increase on CMP server | 16:49 | 6:00
23 | Process CARS size attributes | /www/a/bmcesp/process_size_files.sh | Loads the converted size attributes received from CARS in CMP DB | The latest size attribute details of SKUs will not be avaialble in CMP | 17:15
24 | Image count check on ftp.belk.com | /www/a/bmcesp903/RRD_FILE_COUNT_V2.sh | Script to check the in folder on ftp.belk.com and send a status of the current number of images if the count is > 50 | Support team might loose track of the current count of images on the FTP server. | Every 30 minutes
25 | Keyword Attribute Load | /www/a/bmcesp903/keyword_attrib/bm_keyword.sh | Inserts the keyword attributes for products provided by business into the OBJECT_ATTRIBUTE table | Business team will not be able to see their latest key word changes for products in CMP | 1:00